## FRM_207
|  |  | OPERATIONAL RISK CONTROL SHEET |  |  | Form Code |  | FRM-207
[6 empty] | Revision |  | Rev.01
[6 empty] | Eff. Date |  | 2026-03-23
|  |  | Quality Management System · Controlled Document |  |  | Owner |  | Engineering / QA
|  |  | HESEM Engineering · ISO 9001 / AS9100 · Semiconductor Equipment Parts |  |  | Approved |  | Production Director
1. REFERENCE INFORMATION
Job / WO |  |  |  | Part No. / Revision
Risk Assessment Date |  |  |  | Assessed by
2. RISK EVALUATION
# | Cat. | Risk Item |  |  | Control / Mitigation |  | Result |  | Owner
| TEC | Tight tolerance risk (≤0.025mm features). |  |  | Capable machine + qualified operator assigned.
| TEC | Material risk (new alloy / exotic material). |  |  | Test cut or material trial planned.
| CAP | Capacity risk (machine availability / bottleneck). |  |  | Backup machine identified or schedule buffer.
| CAP | Outsource risk (supplier lead time / quality). |  |  | Qualified backup supplier available.
| QUA | Inspection risk (complex GD&T / CMM required). |  |  | CMM program validated, MSA current.
| QUA | Cleanliness / contamination risk (semi parts). |  |  | Clean process and packaging confirmed.
| OPS | First-time-right risk (new part / new process). |  |  | Trial run or pilot planned before full production.
| OPS | Delivery risk (tight deadline / partial ship). |  |  | Milestone dates confirmed with customer.
3. APPROVAL
Assessed by |  |  |  | Production Director
Name / Signature / Date |  |  |  | Name / Signature / Date
NOTICE — Required for complex / new / tight-tolerance jobs. If any HIGH/CRITICAL → escalate to FRM-209. Ref: SOP-201. Retain: 10 years.
Note on A9: Số công việc Job cần đánh giá rủi ro.
Note on U9: Mã chi tiết / Phiên bản Part đang đánh giá.
Note on A10: Ngày đánh giá Ngày thực hiện đánh giá rủi ro cho job này.
Note on U10: Người đánh giá Engineering Lead hoặc QA thực hiện đánh giá.
Note on A12: Đánh giá rủi ro vận hành Đánh giá rủi ro cụ thể cho job này. Dùng cho job có yếu tố phức tạp, vật liệu mới, dung sai chặt. Nếu có hạng mục HIGH/CRITICAL → chuyển sang FRM-209 High-Risk Review.
Note on F14: Rủi ro dung sai chặt Features có dung sai ≤0.025mm cần máy có năng lực cao. Kiểm tra Cpk của máy cho dung sai tương tự. Operator phải có kinh nghiệm với loại dung sai này.
Note on F15: Rủi ro vật liệu Vật liệu mới hoặc khó gia công (Inconel, Titanium...). Nên trial cut để xác định thông số cắt phù hợp.
Note on F16: Rủi ro năng lực Máy có sẵn trong giai đoạn sản xuất không? Có máy backup nếu máy chính hỏng?
Note on F17: Rủi ro gia công ngoài Nhà cung cấp có đáng tin cậy? Lead time có đủ buffer?
Note on F18: Rủi ro kiểm tra GD&T phức tạp cần CMM. CMM program đã validate chưa? MSA/GRR còn hiệu lực?
Note on F19: Rủi ro ô nhiễm Parts cho semiconductor cần clean process. Xác nhận quy trình làm sạch và đóng gói sạch.
Note on F20: Rủi ro lần đầu Part mới hoặc process mới → trial run trước production. Không sản xuất hàng loạt mà chưa verify process.
Note on F21: Rủi ro giao hàng Deadline chặt → theo dõi milestones hàng ngày. Thỏa thuận partial shipment nếu cần.

## LISTS (hidden)
RESULT | DECISION | STATUS | RISK | YES_NO | DEPT | GATE
PASS | APPROVED | OPEN | LOW | YES | SALES | CONTRACT REVIEW
HOLD | REJECTED | IN PROGRESS | MEDIUM | NO | ENG | FIRST ARTICLE
FAIL | CONDITIONAL | CLOSED | HIGH | NA | PLANNING | IN-PROCESS
NA | ON HOLD | MONITORING | CRITICAL |  | PROD | FINAL
[5 empty] | QA | SHIPPING
PUR
WHS
IT
HR
MGT