## 00_README
HESEM QMS — FORM REBUILD MASTER PLAN V1
Rebaseline form system from scratch based on active SOP + WI + ANNEX. Excel-first, operator-friendly, high-practicality design.
Mục tiêu | Đập đi làm lại toàn bộ kiến trúc FORM theo hướng thực chiến: không duplicate dữ liệu với Epicor, không mơ hồ trách nhiệm, và mọi form phải phục vụ gate/evidence/KPI rõ ràng.
Quyết định kiến trúc | 1) Form logic và file vật lý được tách riêng. 2) Event form = 1 workbook template/record. 3) Log/register = workbook chia theo kỳ hoặc theo bộ phận. 4) Label = workbook in cố định.
Quy mô target set | 115 logical forms: 100 rebuild, 10 new, 1 merge, 1 convert, 2 conditional.
Triết lý thiết kế | Form chỉ ghi evidence/gate/quyết định. Transaction master vẫn ở Epicor. File đã điền và bằng chứng scan/ảnh/PDF lưu ở M365/SharePoint làm SSOT.
Ưu tiên triển khai | Wave 1 ưu tiên các form đi qua mọi job: contract review, traveler, setup, first piece, receiving IQC, NCR/CAPA, final inspection, packaging/ship release.
KPI & nhân sự | Các form có trường owner/user/time/evidence rõ để trở thành nền dữ liệu khách quan cho KPI, thưởng, tăng lương, thăng chức. Không dùng record thiếu bằng chứng cho đánh giá nhân sự.
Tổng logical forms | 115
Rebuild | 100
New | 10
Merge | 1
Convert | 1
Conditional | 2

## 01_ROADMAP
Lộ trình triển khai chi tiết
Triển khai theo phase để giữ chất lượng và giảm rủi ro cutover.
Phase | Task | Description | Owner | Duration | Dependency | Deliverable | Exit_Criteria
P0 | Freeze architecture | Khóa kiến trúc form, mã form, SoR/SSOT, quy tắc version, quy tắc file naming | QMS | 1 tuần | - | Form architecture freeze memo + pack rules | Không còn tranh luận về mã form, owner, nơi lưu, logic version
P0 | Field library | Chuẩn hóa field dictionary, dropdown list, status code, hold code, disposition code, defect code | QMS + QA + IT | 1 tuần | Freeze architecture | Field library v1 | Mọi form dùng cùng tên trường và cùng mã trạng thái
P0 | Boundary cleanup | Chốt boundary form nào là form, form nào là annex, form nào là ERP report | QMS + Process owners | 3 ngày | Freeze architecture | Overlap log signed off | Không còn chồng lấn nhiệm vụ giữa form
P0 | Legacy freeze | Đóng băng HTML form cũ, gắn banner/redirect chỉ đọc | IT + QMS | 3 ngày | Boundary cleanup | Legacy freeze applied | Người dùng không tạo record mới bằng form cũ
P1 | Build core commercial pack | Thiết kế FRM-201/202/203/204/205/207/208/209 trên Excel | Sales + Ops + QMS | 2 tuần | P0 | Wave 1 commercial pack | RFQ → contract review → kickoff → dossier rõ ràng
P1 | Build engineering pack | Thiết kế FRM-301/302/303/304/305/306/311 | Engineering + QA | 2 tuần | P0 | Wave 1 engineering pack | Costing/setup/DFM/FAI có evidence đủ
P1 | Pilot 3 jobs | Chạy thử 3 đơn hàng thật qua bộ form P1 | Sales + ENG + OPS + QA | 1 tuần | Build core commercial pack; Build engineering pack | Pilot report W1 | Không thiếu trường dữ liệu nào để chạy job
P1 | Revise P1 | Sửa form theo pilot | QMS + owners | 3 ngày | Pilot 3 jobs | P1 forms rev B | Tối đa 1 vòng sửa lớn
P2 | Build supplier/material pack | Thiết kế FRM-401~413, 701 | PUR + WHS + QA | 2 tuần | P1 | Wave 2 supplier/material pack | Source control, incoming, hold/disposition rõ
P2 | Build planning/execution pack | Thiết kế FRM-501~504, 511~514, 518, 519 | PLA + OPS + MNT | 2 tuần | P1 | Wave 2 planning/execution pack | Dispatch, setup, pre-run, work transfer có gate rõ
P2 | Pilot supplier/ops | Chạy thử outsource + incoming + dispatch + setup trên 5 job | PUR + QA + OPS | 1 tuần | Build supplier/material pack; Build planning/execution pack | Pilot report W2 | Không còn double entry với Epicor
P3 | Build metrology pack | Thiết kế FRM-601/602/611/612/613 | QA + Metrology | 1 tuần | P2 | Wave 3 metrology pack | Measurement chain và study record đủ bằng chứng
P3 | Build quality release pack | Thiết kế FRM-621/631/641/642/643/651/652/653/654 | QA + OPS | 2 tuần | P2 | Wave 3 quality pack | Sampling, SPC, final release, NCR/CAPA rõ
P3 | Pilot quality pack | Chạy thử trên first piece, IPQC, final inspection, NCR | QA + OPS | 1 tuần | Build quality release pack | Pilot report W3 | Không mù mờ trách nhiệm khi defect/hold
P4 | Build packaging/shipping pack | Thiết kế FRM-702~709, 711~715, 721 | WHS + QA + OPS | 2 tuần | P3 | Wave 4 ship/cleanliness pack | Pack/clean/leak/FOD evidence đủ cho ship release
P4 | Label pack | Thiết kế nhãn FRM-704/705/706 theo print area, barcode/SSCC | WHS + IT | 1 tuần | P4 | Label pack | In nhãn ổn định, không sửa tay
P4 | Pilot ship pack | Chạy thử 5 lô hàng thường + 3 lô clean/vacuum | WHS + QA | 1 tuần | Build packaging/shipping pack | Pilot report W4 | Không sai qty, không sai nhãn, không thiếu bằng chứng
P5 | Build people pack | Thiết kế FRM-801~809 | HR + Dept Managers | 2 tuần | P0 | Wave 5 HR pack | Competency/certification đủ dùng cho tăng lương-thăng chức
P5 | Build HSE/finance pack | Thiết kế FRM-811/812/821 | HSE + Finance | 1 tuần | P0 | Wave 5 support pack | Incident và invoice request rõ
P5 | Build audit/management pack | Thiết kế FRM-901/902/911 | QMS + Top management | 1 tuần | P0 | Wave 5 audit pack | Internal audit, LPA, MR có bằng chứng đủ
P6 | Permissions & template library | Publish template library theo role, khóa sửa template, phân quyền truy cập | IT + QMS | 1 tuần | P1~P5 | Template library online | Người dùng chỉ thấy form đúng role
P6 | Training by role | Đào tạo theo role: Sales/ENG/PUR/OPS/QA/WHS/HR/HSE/FIN | HR + QMS + owners | 2 tuần | Permissions & template library | Training completion record | Ai dùng form nào đều biết form đó
P6 | Cutover plan | Kế hoạch cắt sang form mới, dừng form cũ, map dữ liệu tồn | QMS + IT | 1 tuần | Training by role | Cutover checklist | Ngày cắt rõ, không nhập song song kéo dài
P6 | Go live | Chạy thật toàn bộ form wave đã hoàn thành | All | 1 tuần | Cutover plan | Go-live sign-off | Không còn tạo record mới bằng form cũ
P7 | 30-day stabilization | Theo dõi lỗi dùng form, field thiếu, duplicate entry, resistance points | QMS + IT + owners | 1 tháng | Go live | 30-day stabilization log | Sửa lỗi nhỏ không phá mã form
P7 | KPI extraction | Chốt bộ dữ liệu nào lấy ra KPI, dashboard, pay/promo evidence | QMS + HR + Finance + Dept heads | 2 tuần | Go live | KPI extraction spec | KPI không tranh cãi do lấy đúng nguồn
P7 | Quarterly review | Review hiệu lực form mỗi quý; retire/merge nếu không dùng | QMS + owners | hàng quý | 30-day stabilization | Quarterly form review | Portfolio không phình vô tội vạ

## 02_TARGET_FORMS
Target form portfolio
Logical form catalogue for rebuild from scratch.
target_code | target_file | target_title_vi | family | action | priority | wave | phase | owner | primary_user | form_pattern | workbook_strategy | pack_id | gate_role | linked_sop | linked_wi | linked_annex | sor_ssot | active_doc_refs | compensation_usage | notes
frm-412 | frm-412-receiving-and-iqc-log.html | Nhật ký nhận hàng và IQC | Supplier/Material | MERGE_INTO_FRM-701 | Retire | W0 | Phase 0 - Architecture freeze | Purchasing + QA | Purchasing/QA/WHS | Register / Log | Shared rolling workbook | PACK-PUR-SUPPLIER-REGISTERS | Operational record | SOP-402 |  | ANNEX-PUR-001/002/003 + ANNEX-ENG-002 | M365 evidence / shared workbook | 9 | Governance / compliance record | Duplicate of receiving & IQC log; retire after data migration.
frm-109 | frm-109-access-rights-and-dcr-matrix.html | Ma trận quyền truy cập và DCR | QMS/System | CONVERT_TO_ANNEX+TXN | W0 | W0 | Phase 0 - Architecture freeze | QMS + IT | QMS/IT | Governance matrix | No standalone form; use FRM-141 + FRM-111 + ANNEX-QMS-025/IT-001 | FRM-109 | System control / governance | SOP-104 |  | ANNEX-QMS-005/006/012/019/021 + ANNEX-IT-001/002 | M365 / access control / audit evidence | 2 | Governance / compliance record | Avoid duplicate manual maintenance of authority/access matrix.
frm-202 | frm-202-contract-review-checklist.html | Checklist xem xét hợp đồng | Customer/Commercial | REBUILD | P1 | W1 | Phase 1 - Core commercial & engineering | Sales + Ops | Sales/Ops/Planner | Checklist / Gate | Single template workbook | FRM-202 | Gate / Hold / Release | SOP-201 | WI-201/WI-202/WI-203/WI-207 | ANNEX-QMS-020 + ANNEX-QMS-008 | Epicor transaction + M365 evidence | 16 | Indirect evidence / governance
frm-203 | frm-203-job-traveler.html | Phiếu theo dõi Job | Customer/Commercial | REBUILD | P1 | W1 | Phase 1 - Core commercial & engineering | Sales + Ops | Sales/Ops/Planner | Event form | Single template workbook | FRM-203 | Operational record / KPI evidence | SOP-201 | WI-201/WI-202/WI-203/WI-207 | ANNEX-QMS-004/008/020 + ANNEX-OPS-002 | Epicor transaction + M365 evidence | 15 | Indirect evidence / governance
frm-205 | frm-205-job-dossier-evidence-index.html | Job Dossier Evidence Index | Customer/Commercial | NEW | P1 | W1 | Phase 1 - Core commercial & engineering | Sales + Ops | Sales/Ops/Planner | Register / Log | Single template workbook | FRM-205 | Operational record | SOP-201 | WI-203 | ANNEX-QMS-004/005/019/021 | M365 evidence / shared workbook | 0 | Governance / compliance record | Missing critical record for dossier completeness and evidence handoff.
frm-208 | frm-208-daily-tier-meeting-and-escalation-log.html | Daily Tier Meeting and Escalation Log | Customer/Commercial | NEW | P1 | W1 | Phase 1 - Core commercial & engineering | Sales + Ops | Sales/Ops/Planner | Review / meeting record | Shared rolling workbook | PACK-OPS-TIER-MEETING | Gate / Hold / Release | SOP-201/SOP-501 | WI-202 | ANNEX-QMS-008/009/020 | M365 evidence / shared workbook | 0 | Governance / compliance record | Needed to operationalize tier meetings, action closure, and escalation evidence.
frm-302 | frm-302-setup-sheet.html | Phiếu setup | Engineering | REBUILD | P1 | W1 | Phase 1 - Core commercial & engineering | Engineering | Engineering | Event form | Single template workbook | FRM-302 | Gate / Hold / Release | SOP-301 | WI-302/WI-517/WI-519 | ANNEX-ENG-001/002 + ANNEX-QA-003/004 | Epicor transaction + M365 evidence | 23 | Indirect evidence / governance
frm-306 | frm-306-engineering-release-and-baseline-package-approval.html | Engineering Release and Baseline Package Approval | Engineering | NEW | P1 | W1 | Phase 1 - Core commercial & engineering | Engineering | Engineering | Checklist / Gate | Single template workbook | FRM-306 | Gate / Hold / Release | SOP-303 | WI-302/WI-519 | ANNEX-ENG-001/002 + ANNEX-QMS-004/005 | M365 evidence / shared workbook | 0 | Governance / compliance record | Missing baseline release evidence for package freeze, revision alignment, and job snapshot.
frm-502 | frm-502-daily-dispatch-list.html | Danh sách dispatch hằng ngày | Planning/Production/Maintenance | REBUILD | P1 | W1 | Phase 1 - Core commercial & engineering | Production Control | Planner/Production | Event form | Single template workbook | FRM-502 | Operational record / KPI evidence | SOP-501/SOP-502 | WI-501 | ANNEX-OPS-001/002 + ANNEX-QMS-008/020 | Epicor transaction + M365 evidence | 14 | Direct KPI / bonus / promotion evidence
frm-511 | frm-511-setup-and-first-piece-record.html | Biên bản setup và first piece | Planning/Production/Maintenance | REBUILD | P1 | W1 | Phase 1 - Core commercial & engineering | Production Control | Planner/Production | Event form | Single template workbook | FRM-511 | Gate / Hold / Release | SOP-504 | WI-517/WI-519 | ANNEX-ENG-001 + ANNEX-QMS-017 | Epicor transaction + M365 evidence | 17 | Direct KPI / bonus / promotion evidence
frm-519 | frm-519-job-packet-quick-check-and-pre-run-verification.html | Job Packet Quick Check and Pre-Run Verification | Planning/Production/Maintenance | NEW | P1 | W1 | Phase 1 - Core commercial & engineering | Production Control | Planner/Production | Checklist / Gate | Single template workbook | FRM-519 | Gate / Hold / Release | SOP-504 | WI-519 | ANNEX-ENG-001 + ANNEX-QMS-014 | M365 evidence / shared workbook | 0 | Indirect evidence / governance | Needed to prevent wrong rev/wrong tool/wrong program before spindle start.
frm-631 | frm-631-spc-and-capability-log.html | Nhật ký SPC và năng lực quá trình | Quality/Metrology | REBUILD | P1 | W1 | Phase 1 - Core commercial & engineering | QA | QA/IPQC/OQC | Register / Log | Shared rolling workbook | PACK-QA-ROLLING-LOGS | Operational record / KPI evidence | SOP-604 | WI-604 | ANNEX-QA-001/002/003/004/006/007 + ANNEX-QMS-020 | Epicor transaction + M365 evidence | 21 | Direct KPI / bonus / promotion evidence
frm-641 | frm-641-final-inspection-report.html | Báo cáo kiểm tra cuối | Quality/Metrology | REBUILD | P1 | W1 | Phase 1 - Core commercial & engineering | QA | QA/IPQC/OQC | Event form | Single template workbook | FRM-641 | Gate / Hold / Release | SOP-605 | WI-605 | ANNEX-QA-001/002/003/004/006/007 + ANNEX-QMS-020 | Epicor transaction + M365 evidence | 20 | Direct KPI / bonus / promotion evidence
frm-651 | frm-651-nonconformance-report.html | Báo cáo NCR | Quality/Metrology | REBUILD | P1 | W1 | Phase 1 - Core commercial & engineering | QA | QA/IPQC/OQC | Event form | Single template workbook | FRM-651 | Gate / Hold / Release | SOP-606 | WI-606 | ANNEX-QA-001/002/003/004/006/007 + ANNEX-QMS-020 | M365 evidence / shared workbook | 57 | Direct KPI / bonus / promotion evidence
frm-652 | frm-652-capa-8d-report.html | Báo cáo CAPA / 8D | Quality/Metrology | REBUILD | P1 | W1 | Phase 1 - Core commercial & engineering | QA | QA/IPQC/OQC | Event form | Single template workbook | FRM-652 | Gate / Hold / Release | SOP-606 | WI-606 | ANNEX-QA-001/002/003/004/006/007 + ANNEX-QMS-020 | M365 evidence / shared workbook | 49 | Direct KPI / bonus / promotion evidence
frm-701 | frm-701-receiving-and-iqc-log.html | Nhật ký nhận hàng và IQC | Warehouse/Cleanliness/Shipment | REBUILD | P1 | W1 | Phase 1 - Core commercial & engineering | Warehouse + QA | WHS/QA/Production | Register / Log | Shared rolling workbook | PACK-WHS-ROLLING-LOGS | Gate / Hold / Release | SOP-701 | WI-701 | ANNEX-WHS-001/002 + ANNEX-QMS-007/014/017 | Epicor transaction + M365 evidence | 21 | Direct KPI / bonus / promotion evidence
frm-707 | frm-707-packaging-checklist.html | Checklist đóng gói | Warehouse/Cleanliness/Shipment | REBUILD | P1 | W1 | Phase 1 - Core commercial & engineering | Warehouse + QA | WHS/QA/Production | Checklist / Gate | Single template workbook | FRM-707 | Gate / Hold / Release | SOP-703 | WI-206/WI-714 | ANNEX-WHS-001/002 + ANNEX-QMS-007/014/017 | Epicor transaction + M365 evidence | 20 | Direct KPI / bonus / promotion evidence
frm-209 | frm-209-high-risk-job-readiness-review.html | High-Risk Job Readiness Review | Customer/Commercial | NEW | P1 | W2 | Phase 2 - Supplier, material, planning | Sales + Ops | Sales/Ops/Planner | Checklist / Gate | Single template workbook | FRM-209 | Gate / Hold / Release | SOP-201/SOP-501 | WI-207 | ANNEX-QMS-020/OPS-002/QA-003 | M365 evidence / shared workbook | 0 | Governance / compliance record | Needed for red/high-risk jobs with multi-gate review before release.
frm-501 | frm-501-planning-release-checklist.html | Checklist phát hành kế hoạch | Planning/Production/Maintenance | REBUILD | P1 | W2 | Phase 2 - Supplier, material, planning | Production Control | Planner/Production | Checklist / Gate | Single template workbook | FRM-501 | Gate / Hold / Release | SOP-501/SOP-502 | WI-501 | ANNEX-OPS-001/002 + ANNEX-QMS-008/020 | Epicor transaction + M365 evidence | 12 | Indirect evidence / governance
frm-503 | frm-503-wip-aging-report.html | Báo cáo WIP aging | Planning/Production/Maintenance | REBUILD | P1 | W2 | Phase 2 - Supplier, material, planning | Production Control | Planner/Production | Event form | Single template workbook | FRM-503 | Operational record / KPI evidence | SOP-501/SOP-502 | WI-501 | ANNEX-OPS-001/002 + ANNEX-QMS-008/020 | Epicor transaction + M365 evidence | 15 | Direct KPI / bonus / promotion evidence
frm-504 | frm-504-shift-handover-log.html | Nhật ký bàn giao ca | Planning/Production/Maintenance | REBUILD | P1 | W2 | Phase 2 - Supplier, material, planning | Production Control | Planner/Production | Register / Log | Shared rolling workbook | PACK-OPS-DAILY-LOGS | Operational record / KPI evidence | SOP-501/SOP-502 | WI-501 | ANNEX-OPS-001/002 + ANNEX-QMS-008/020 | Epicor transaction + M365 evidence | 12 | Direct KPI / bonus / promotion evidence
frm-518 | frm-518-work-transfer-validation-record.html | Work Transfer Validation Record | Planning/Production/Maintenance | NEW | P1 | W2 | Phase 2 - Supplier, material, planning | Production Control | Planner/Production | Checklist / Gate | Single template workbook | FRM-518 | Gate / Hold / Release | SOP-504 | WI-518 | ANNEX-ENG-001 + ANNEX-OPS-002 | M365 evidence / shared workbook | 0 | Indirect evidence / governance | Needed to validate machine/cell/shift transfer without losing first-pass quality.
frm-602 | frm-602-gage-verification-log.html | Nhật ký xác minh thiết bị đo | Quality/Metrology | REBUILD | P1 | W2 | Phase 2 - Supplier, material, planning | QA | QA/IPQC/OQC | Register / Log | Shared rolling workbook | PACK-QA-ROLLING-LOGS | Operational record / KPI evidence | SOP-601 | WI-602 | ANNEX-QA-001/002/003/004/006/007 + ANNEX-QMS-020 | Calibration / QA file + M365 evidence | 5 | Indirect evidence / governance
frm-621 | frm-621-aql-inspection-record.html | Biên bản kiểm tra AQL | Quality/Metrology | REBUILD | P1 | W2 | Phase 2 - Supplier, material, planning | QA | QA/IPQC/OQC | Event form | Single template workbook | FRM-621 | Gate / Hold / Release | SOP-603 | WI-603 | ANNEX-QA-001/002/003/004/006/007 + ANNEX-QMS-020 | Epicor transaction + M365 evidence | 10 | Direct KPI / bonus / promotion evidence
frm-642 | frm-642-final-inspection-and-coc-register.html | Sổ final inspection và COC | Quality/Metrology | REBUILD | P1 | W2 | Phase 2 - Supplier, material, planning | QA | QA/IPQC/OQC | Register / Log | Shared rolling workbook | PACK-QA-ROLLING-LOGS | Gate / Hold / Release | SOP-605 | WI-605 | ANNEX-QA-001/002/003/004/006/007 + ANNEX-QMS-020 | Epicor transaction + M365 evidence | 15 | Governance / compliance record
frm-403 | frm-403-outsourced-processing-request.html | Yêu cầu thuê ngoài công đoạn | Supplier/Material | REBUILD | P1 | W2 | Phase 2 - Supplier, material, planning | Purchasing + QA | Purchasing/QA/WHS | Event form | Single template workbook | FRM-403 | Gate / Hold / Release | SOP-401 | WI-206 | ANNEX-PUR-001/002/003 + ANNEX-ENG-002 | Epicor transaction + M365 evidence | 15 | Indirect evidence / governance
frm-405 | frm-405-supplier-scorecard.html | Scorecard NCC | Supplier/Material | REBUILD | P1 | W2 | Phase 2 - Supplier, material, planning | Purchasing + QA | Purchasing/QA/WHS | Print label / card | Print workbook | PACK-WHS-LABELS | Operational record | SOP-401 |  | ANNEX-PUR-001/002/003 + ANNEX-ENG-002 | M365 evidence / shared workbook | 15 | Indirect evidence / governance
frm-406 | frm-406-supplier-corrective-action-request.html | SCAR | Supplier/Material | REBUILD | P1 | W2 | Phase 2 - Supplier, material, planning | Purchasing + QA | Purchasing/QA/WHS | Event form | Single template workbook | FRM-406 | Operational record | SOP-401 |  | ANNEX-PUR-001/002/003 + ANNEX-ENG-002 | M365 evidence / shared workbook | 16 | Indirect evidence / governance
frm-413 | frm-413-hold-and-disposition-log.html | Nhật ký HOLD và disposition | Supplier/Material | REBUILD | P1 | W2 | Phase 2 - Supplier, material, planning | Purchasing + QA | Purchasing/QA/WHS | Register / Log | Shared rolling workbook | PACK-PUR-SUPPLIER-REGISTERS | Operational record | SOP-402 |  | ANNEX-PUR-001/002/003 + ANNEX-ENG-002 | M365 evidence / shared workbook | 15 | Indirect evidence / governance
frm-709 | frm-709-clean-packaging-checklist.html | Clean Checklist đóng gói | Warehouse/Cleanliness/Shipment | REBUILD | P1 | W2 | Phase 2 - Supplier, material, planning | Warehouse + QA | WHS/QA/Production | Checklist / Gate | Single template workbook | FRM-709 | Gate / Hold / Release | SOP-702 | WI-714 | ANNEX-WHS-001/002 + ANNEX-QMS-007/014/017 | Epicor transaction + M365 evidence | 15 | Direct KPI / bonus / promotion evidence
frm-712 | frm-712-helium-leak-test-record.html | Biên bản helium leak test | Warehouse/Cleanliness/Shipment | REBUILD | P1 | W2 | Phase 2 - Supplier, material, planning | Warehouse + QA | WHS/QA/Production | Event form | Single template workbook | FRM-712 | Gate / Hold / Release | SOP-702 | WI-715 | ANNEX-WHS-001/002 + ANNEX-QMS-007/014/017 | Epicor transaction + M365 evidence | 8 | Direct KPI / bonus / promotion evidence
frm-401 | frm-401-po-tracker.html | Theo dõi PO | Supplier/Material | REBUILD_AS_EXCEPTION_LOG | P2 | W2 | Phase 2 - Supplier, material, planning | Purchasing + QA | Purchasing/QA/WHS | Register / Log | Shared rolling workbook | PACK-PUR-EXCEPTION | Operational record | SOP-401 |  | ANNEX-PUR-001/002/003 + ANNEX-ENG-002 | Epicor transaction + M365 evidence | 10 | Governance / compliance record | Do not duplicate Epicor PO master; keep only expedite/exception/risk events.
frm-201 | frm-201-rfq-register.html | Sổ RFQ | Customer/Commercial | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Sales + Ops | Sales/Ops/Planner | Register / Log | Shared rolling workbook | PACK-SAL-RFQ | Operational record | SOP-201 |  |  | Epicor transaction + M365 evidence | 12 | Governance / compliance record
frm-204 | frm-204-job-kickoff-checklist.html | Checklist kickoff đơn hàng | Customer/Commercial | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Sales + Ops | Sales/Ops/Planner | Checklist / Gate | Single template workbook | FRM-204 | Gate / Hold / Release | SOP-201 | WI-201/WI-202/WI-203/WI-207 | ANNEX-QMS-004/008/020 + ANNEX-OPS-002 | Epicor transaction + M365 evidence | 14 | Indirect evidence / governance
frm-206 | frm-206-job-completion-checklist.html | Checklist hoàn tất job | Customer/Commercial | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Sales + Ops | Sales/Ops/Planner | Checklist / Gate | Single template workbook | FRM-206 | Operational record | SOP-201 | WI-201/WI-202/WI-203/WI-207 | ANNEX-QMS-004/008/020 + ANNEX-OPS-002 | Epicor transaction + M365 evidence | 9 | Governance / compliance record
frm-207 | frm-207-operational-risk-management-worksheet.html | Phiếu quản trị rủi ro vận hành | Customer/Commercial | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Sales + Ops | Sales/Ops/Planner | Event form | Single template workbook | FRM-207 | Gate / Hold / Release | SOP-201 | WI-201/WI-202/WI-203/WI-207 | ANNEX-QMS-020 + ANNEX-QMS-008 | Epicor transaction + M365 evidence | 5 | Governance / compliance record
frm-211 | frm-211-complaint-log.html | Nhật ký khiếu nại | Customer/Commercial | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Sales + QA | Sales/QA | Register / Log | Shared rolling workbook | PACK-SAL-COMMERCIAL-REGISTERS | Operational record | SOP-202 | WI-201/WI-202/WI-203/WI-207 |  | M365 evidence / shared workbook | 8 | Governance / compliance record
frm-212 | frm-212-customer-change-request.html | Yêu cầu thay đổi từ khách hàng | Customer/Commercial | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Sales + QA | Sales/QA | Event form | Single template workbook | FRM-212 | Operational record | SOP-202 | WI-201/WI-202/WI-203/WI-207 |  | M365 evidence / shared workbook | 5 | Governance / compliance record
frm-213 | frm-213-rma-tracking-log.html | Nhật ký theo dõi RMA | Customer/Commercial | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Sales + QA | Sales/QA | Register / Log | Shared rolling workbook | PACK-SAL-COMMERCIAL-REGISTERS | Operational record | SOP-202 | WI-201/WI-202/WI-203/WI-207 |  | M365 evidence / shared workbook | 5 | Governance / compliance record
frm-221 | frm-221-customer-property-register.html | Sổ tài sản của khách hàng | Customer/Commercial | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Sales + QA | Sales/QA | Register / Log | Shared rolling workbook | PACK-SAL-COMMERCIAL-REGISTERS | Operational record | SOP-203 |  |  | M365 evidence / shared workbook | 1 | Governance / compliance record
frm-301 | frm-301-costing-sheet.html | Phiếu costing | Engineering | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Engineering | Engineering | Event form | Single template workbook | FRM-301 | Gate / Hold / Release | SOP-301 | WI-302/WI-517/WI-519 | ANNEX-ENG-001/002 + ANNEX-QA-003/004 | Epicor transaction + M365 evidence | 10 | Indirect evidence / governance
frm-303 | frm-303-dfm-review-checklist.html | Checklist DFM Review | Engineering | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Engineering | Engineering | Checklist / Gate | Single template workbook | FRM-303 | Gate / Hold / Release | SOP-301 | WI-302/WI-517/WI-519 | ANNEX-ENG-001/002 + ANNEX-QA-003/004 | Epicor transaction + M365 evidence | 7 | Indirect evidence / governance
frm-304 | frm-304-semiconductor-part-classification.html | Phân loại part bán dẫn | Engineering | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Engineering | Engineering | Event form | Single template workbook | FRM-304 | Gate / Hold / Release | SOP-301/SOP-303 | WI-302/WI-517/WI-519 | ANNEX-ENG-001/002 + ANNEX-QA-003/004 | Epicor transaction + M365 evidence | 4 | Governance / compliance record
frm-305 | frm-305-inspection-program-release-checklist.html | Checklist phát hành chương trình kiểm tra | Engineering | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Engineering | Engineering | Checklist / Gate | Single template workbook | FRM-305 | Gate / Hold / Release | SOP-301/SOP-303 | WI-302/WI-517/WI-519 | ANNEX-ENG-001/002 + ANNEX-QA-003/004 | Epicor transaction + M365 evidence | 19 | Indirect evidence / governance
frm-311 | frm-311-fai-report.html | Báo cáo FAI | Engineering | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Engineering | Engineering | Event form | Single template workbook | FRM-311 | Gate / Hold / Release | SOP-302 | WI-302/WI-517/WI-519 |  | Epicor transaction + M365 evidence | 12 | Indirect evidence / governance
frm-512 | frm-512-downtime-log.html | Nhật ký downtime | Planning/Production/Maintenance | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Production Control | Planner/Production | Register / Log | Shared rolling workbook | PACK-OPS-DAILY-LOGS | Operational record / KPI evidence | SOP-501/SOP-502 | WI-516 | ANNEX-ENG-001 + ANNEX-QMS-017 | Epicor transaction + M365 evidence | 11 | Direct KPI / bonus / promotion evidence
frm-513 | frm-513-tool-life-log.html | Nhật ký tuổi dao | Planning/Production/Maintenance | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Production Control | Planner/Production | Register / Log | Shared rolling workbook | PACK-OPS-DAILY-LOGS | Operational record / KPI evidence | SOP-501/SOP-502 | WI-516 | ANNEX-ENG-001 + ANNEX-QMS-017 | Epicor transaction + M365 evidence | 13 | Direct KPI / bonus / promotion evidence
frm-514 | frm-514-smed-changeover-sheet.html | SMED | Planning/Production/Maintenance | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Production Control | Planner/Production | Event form | Single template workbook | FRM-514 | Operational record | SOP-504 | WI-517/WI-519 | ANNEX-ENG-001 + ANNEX-QMS-017 | Epicor transaction + M365 evidence | 4 | Governance / compliance record
frm-521 | frm-521-pm-checklist.html | Checklist PM | Planning/Production/Maintenance | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Maintenance | Production/Maintenance | Checklist / Gate | Single template workbook | FRM-521 | Operational record / KPI evidence | SOP-503 |  | ANNEX-HSE-001 + ANNEX-QMS-025 | M365 evidence / shared workbook | 3 | Direct KPI / bonus / promotion evidence
frm-522 | frm-522-crash-report.html | Báo cáo crash | Planning/Production/Maintenance | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Maintenance | Production/Maintenance | Event form | Single template workbook | FRM-522 | Operational record / KPI evidence | SOP-503 |  | ANNEX-HSE-001 + ANNEX-QMS-025 | M365 evidence / shared workbook | 3 | Direct KPI / bonus / promotion evidence
frm-523 | frm-523-tooling-register.html | Sổ tooling | Planning/Production/Maintenance | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Maintenance | Production/Maintenance | Register / Log | Shared rolling workbook | PACK-OPS-DAILY-LOGS | Operational record / KPI evidence | SOP-503 |  | ANNEX-HSE-001 + ANNEX-QMS-025 | M365 evidence / shared workbook | 2 | Governance / compliance record
frm-524 | frm-524-machine-history-log.html | Lịch sử máy | Planning/Production/Maintenance | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Maintenance | Production/Maintenance | Register / Log | Shared rolling workbook | PACK-OPS-DAILY-LOGS | Operational record / KPI evidence | SOP-503 |  | ANNEX-HSE-001 + ANNEX-QMS-025 | M365 evidence / shared workbook | 2 | Governance / compliance record
frm-525 | frm-525-gage-equipment-inventory.html | Danh mục thiết bị đo | Planning/Production/Maintenance | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Maintenance | Production/Maintenance | Register / Log | Shared rolling workbook | PACK-OPS-DAILY-LOGS | Operational record / KPI evidence | SOP-503 |  | ANNEX-HSE-001 + ANNEX-QMS-025 | M365 evidence / shared workbook | 5 | Governance / compliance record
frm-101 | frm-101-master-document-register.html | Sổ đăng ký tài liệu gốc | QMS/System | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | QMS | QMS/Process Owner | Register / Log | Shared rolling workbook | PACK-QMS-GOVERNANCE-REGISTERS | System control / governance | SOP-101/SOP-102 |  |  | M365 evidence / shared workbook | 0 | Governance / compliance record
frm-102 | frm-102-document-change-request.html | Yêu cầu thay đổi tài liệu | QMS/System | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | QMS | QMS/Process Owner | Event form | Single template workbook | FRM-102 | System control / governance | SOP-101/SOP-102 |  |  | M365 evidence / shared workbook | 14 | Governance / compliance record
frm-104 | frm-104-document-implementation-checklist.html | Checklist triển khai tài liệu | QMS/System | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | QMS | QMS/Process Owner | Checklist / Gate | Single template workbook | FRM-104 | System control / governance | SOP-101/SOP-102 |  |  | M365 evidence / shared workbook | 0 | Governance / compliance record
frm-105 | frm-105-peer-review-log.html | Nhật ký peer review | QMS/System | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | QMS | QMS/Process Owner | Register / Log | Shared rolling workbook | PACK-QMS-GOVERNANCE-REGISTERS | System control / governance | SOP-101/SOP-102 |  |  | M365 evidence / shared workbook | 4 | Governance / compliance record
frm-106 | frm-106-pilot-run-log.html | Nhật ký pilot/dry-run | QMS/System | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | QMS | QMS/Process Owner | Register / Log | Shared rolling workbook | PACK-QMS-GOVERNANCE-REGISTERS | System control / governance | SOP-101/SOP-102 |  |  | M365 evidence / shared workbook | 1 | Governance / compliance record
frm-110 | frm-110-m365-configuration-checklist.html | Checklist cấu hình M365 | QMS/System | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | QMS + IT | QMS/IT | Checklist / Gate | Single template workbook | FRM-110 | System control / governance | SOP-104 |  | ANNEX-QMS-005/006/012/019/021 + ANNEX-IT-001/002 | M365 / access control / audit evidence | 5 | Governance / compliance record
frm-111 | frm-111-quarterly-access-review.html | Rà soát quyền truy cập hàng quý | QMS/System | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | QMS + IT | QMS/IT | Event form | Single template workbook | FRM-111 | System control / governance | SOP-104 |  | ANNEX-QMS-005/006/012/019/021 + ANNEX-IT-001/002 | M365 / access control / audit evidence | 9 | Governance / compliance record
frm-131 | frm-131-risk-and-opportunity-register.html | Sổ đăng ký rủi ro và cơ hội | QMS/System | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | QMS | QMS/Process Owner | Event form | Single template workbook | FRM-131 | System control / governance | SOP-103 |  | ANNEX-QA-004/006 + ANNEX-QMS-027 | M365 evidence / shared workbook | 9 | Governance / compliance record
frm-132 | frm-132-pfmea-lite-aiag-format.html | PFMEA Lite | QMS/System | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | QMS | QMS/Process Owner | Event form | Single template workbook | FRM-132 | System control / governance | SOP-103 |  | ANNEX-QA-004/006 + ANNEX-QMS-027 | M365 evidence / shared workbook | 6 | Governance / compliance record
frm-133 | frm-133-control-plan.html | Control Plan | QMS/System | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | QMS | QMS/Process Owner | Event form | Single template workbook | FRM-133 | System control / governance | SOP-103 |  | ANNEX-QA-004/006 + ANNEX-QMS-027 | M365 evidence / shared workbook | 8 | Governance / compliance record
frm-141 | frm-141-it-access-request-change-revocation.html | Yêu cầu / thay đổi / thu hồi quyền IT | QMS/System | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | QMS + IT | QMS/IT | Event form | Single template workbook | FRM-141 | System control / governance | SOP-104 |  | ANNEX-QMS-005/006/012/019/021 + ANNEX-IT-001/002 | M365 / access control / audit evidence | 7 | Governance / compliance record
frm-151 | frm-151-lessons-learned-log.html | Nhật ký bài học kinh nghiệm | QMS/System | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | QMS | QMS/Process Owner | Register / Log | Shared rolling workbook | PACK-QMS-GOVERNANCE-REGISTERS | System control / governance | SOP-105/SOP-903 |  |  | M365 evidence / shared workbook | 12 | Governance / compliance record
frm-161 | frm-161-ecr-eco.html | ECR / ECO | QMS/System | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | QMS | QMS/Process Owner | Event form | Single template workbook | FRM-161 | System control / governance | SOP-106 |  | ANNEX-QMS-023 + ANNEX-QMS-025/026 | M365 evidence / shared workbook | 0 | Governance / compliance record
frm-162 | frm-162-change-impact-matrix.html | Ma trận tác động thay đổi | QMS/System | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | QMS | QMS/Process Owner | Event form | Single template workbook | FRM-162 | System control / governance | SOP-106 |  | ANNEX-QMS-023 + ANNEX-QMS-025/026 | M365 evidence / shared workbook | 8 | Governance / compliance record
frm-163 | frm-163-configuration-audit-checklist.html | Checklist audit cấu hình | QMS/System | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | QMS | QMS/Process Owner | Checklist / Gate | Single template workbook | FRM-163 | System control / governance | SOP-106 |  | ANNEX-QMS-023 + ANNEX-QMS-025/026 | M365 evidence / shared workbook | 6 | Governance / compliance record
frm-171 | frm-171-communication-plan-and-log.html | Kế hoạch và nhật ký truyền thông | QMS/System | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | QMS | QMS/Process Owner | Register / Log | Shared rolling workbook | PACK-QMS-GOVERNANCE-REGISTERS | System control / governance | SOP-107 |  | ANNEX-QMS-009/020 | M365 evidence / shared workbook | 5 | Governance / compliance record
frm-181 | frm-181-contingency-event-log.html | Nhật ký sự kiện gián đoạn | QMS/System | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | QMS | QMS/Process Owner | Event form | Single template workbook | FRM-181 | System control / governance | SOP-108 |  | ANNEX-QMS-020/021 | M365 evidence / shared workbook | 4 | Governance / compliance record
frm-601 | frm-601-calibration-log.html | Nhật ký hiệu chuẩn | Quality/Metrology | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | QA | QA/IPQC/OQC | Register / Log | Shared rolling workbook | PACK-QA-ROLLING-LOGS | Operational record / KPI evidence | SOP-601 | WI-602 | ANNEX-QA-001/002/003/004/006/007 + ANNEX-QMS-020 | Calibration / QA file + M365 evidence | 5 | Governance / compliance record
frm-611 | frm-611-grr-study-form.html | GR&R Study Form | Quality/Metrology | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | QA | QA/IPQC/OQC | Event form | MSA workbook pack | PACK-QA-MSA | Operational record / KPI evidence | SOP-602 | WI-602 | ANNEX-QA-001/002/003/004/006/007 + ANNEX-QMS-020 | Calibration / QA file + M365 evidence | 10 | Indirect evidence / governance
frm-612 | frm-612-bias-linearity-stability-study-form.html | Biểu mẫu bias/linearity/stability | Quality/Metrology | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | QA | QA/IPQC/OQC | Event form | MSA workbook pack | PACK-QA-MSA | Operational record / KPI evidence | SOP-602 | WI-602 | ANNEX-QA-001/002/003/004/006/007 + ANNEX-QMS-020 | Calibration / QA file + M365 evidence | 3 | Indirect evidence / governance
frm-613 | frm-613-attribute-msa-and-cmm-qualification-record.html | Hồ sơ MSA thuộc tính và qualification CMM | Quality/Metrology | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | QA | QA/IPQC/OQC | Event form | MSA workbook pack | PACK-QA-MSA | Operational record / KPI evidence | SOP-602 | WI-602 | ANNEX-QA-001/002/003/004/006/007 + ANNEX-QMS-020 | Calibration / QA file + M365 evidence | 5 | Indirect evidence / governance
frm-643 | frm-643-safety-special-characteristics-register.html | Sổ đặc tính an toàn/đặc biệt | Quality/Metrology | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | QA | QA/IPQC/OQC | Register / Log | Shared rolling workbook | PACK-QA-ROLLING-LOGS | Operational record | SOP-605 |  | ANNEX-QA-001/002/003/004/006/007 + ANNEX-QMS-020 | M365 evidence / shared workbook | 6 | Governance / compliance record
frm-653 | frm-653-a3-pdca-report.html | A3/PDCA | Quality/Metrology | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | QA | QA/IPQC/OQC | Event form | Single template workbook | FRM-653 | Operational record | SOP-606 | WI-606 | ANNEX-QA-001/002/003/004/006/007 + ANNEX-QMS-020 | M365 evidence / shared workbook | 11 | Governance / compliance record
frm-654 | frm-654-customer-satisfaction-survey.html | Khảo sát hài lòng khách hàng | Quality/Metrology | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | QA | QA/IPQC/OQC | Review / meeting record | Single template workbook | FRM-654 | Operational record | SOP-606 |  |  | M365 evidence / shared workbook | 5 | Governance / compliance record
frm-402 | frm-402-supplier-evaluation.html | Đánh giá nhà cung cấp | Supplier/Material | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Purchasing + QA | Purchasing/QA/WHS | Event form | Single template workbook | FRM-402 | Operational record | SOP-401 |  | ANNEX-PUR-001/002/003 + ANNEX-ENG-002 | M365 evidence / shared workbook | 14 | Governance / compliance record
frm-404 | frm-404-outsourced-dispatch-checklist.html | Checklist dispatch outsource | Supplier/Material | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Purchasing + QA | Purchasing/QA/WHS | Checklist / Gate | Single template workbook | FRM-404 | Gate / Hold / Release | SOP-401 | WI-206 | ANNEX-PUR-001/002/003 + ANNEX-ENG-002 | Epicor transaction + M365 evidence | 13 | Governance / compliance record
frm-408 | frm-408-flowdown-requirements-checklist.html | Checklist flow-down yêu cầu | Supplier/Material | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Purchasing + QA | Purchasing/QA/WHS | Checklist / Gate | Single template workbook | FRM-408 | Operational record | SOP-401 |  | ANNEX-PUR-001/002/003 + ANNEX-ENG-002 | M365 evidence / shared workbook | 2 | Governance / compliance record
frm-409 | frm-409-supplier-audit-checklist.html | Checklist audit NCC | Supplier/Material | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Purchasing + QA | Purchasing/QA/WHS | Checklist / Gate | Single template workbook | FRM-409 | Operational record | SOP-401 |  | ANNEX-PUR-001/002/003 + ANNEX-ENG-002 | M365 evidence / shared workbook | 3 | Governance / compliance record
frm-411 | frm-411-outsourced-processing-incoming-inspection.html | Kiểm tra đầu vào hàng thuê ngoài | Supplier/Material | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Purchasing + QA | Purchasing/QA/WHS | Event form | Single template workbook | FRM-411 | Gate / Hold / Release | SOP-402 |  | ANNEX-PUR-001/002/003 + ANNEX-ENG-002 | Epicor transaction + M365 evidence | 17 | Indirect evidence / governance
frm-702 | frm-702-shipping-checklist.html | Checklist giao hàng | Warehouse/Cleanliness/Shipment | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Warehouse + QA | WHS/QA/Production | Checklist / Gate | Single template workbook | FRM-702 | Gate / Hold / Release | SOP-701/702/703 | WI-206/WI-714 | ANNEX-WHS-001/002 + ANNEX-QMS-007/014/017 | Epicor transaction + M365 evidence | 21 | Direct KPI / bonus / promotion evidence
frm-703 | frm-703-wip-card.html | Thẻ WIP | Warehouse/Cleanliness/Shipment | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Warehouse + QA | WHS/QA/Production | Print label / card | Print workbook | PACK-WHS-LABELS | Operational record / KPI evidence | SOP-701 | WI-702 | ANNEX-WHS-001/002 + ANNEX-QMS-007/014/017 | Epicor transaction + M365 evidence | 16 | Governance / compliance record
frm-708 | frm-708-environmental-log.html | Nhật ký môi trường | Warehouse/Cleanliness/Shipment | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Warehouse + QA | WHS/QA/Production | Register / Log | Shared rolling workbook | PACK-WHS-ROLLING-LOGS | Operational record / KPI evidence | SOP-701 | WI-702 | ANNEX-WHS-001/002 + ANNEX-QMS-007/014/017 | M365 evidence / shared workbook | 14 | Direct KPI / bonus / promotion evidence
frm-711 | frm-711-cleanliness-verification-form.html | Biểu mẫu xác nhận độ sạch | Warehouse/Cleanliness/Shipment | REBUILD | P2 | W3 | Phase 3 - Production, maintenance, metrology | Warehouse + QA | WHS/QA/Production | Event form | Single template workbook | FRM-711 | Gate / Hold / Release | SOP-702 | WI-711 | ANNEX-WHS-001/002 + ANNEX-QMS-007/014/017 | M365 evidence / shared workbook | 11 | Governance / compliance record
frm-704 | frm-704-part-id-label.html | Nhãn part ID | Warehouse/Cleanliness/Shipment | REBUILD | P2 | W4 | Phase 4 - Cleanliness, packaging, shipping | Warehouse + QA | WHS/QA/Production | Print label / card | Labels workbook pack | PACK-WHS-LABELS | Operational record | SOP-703 |  | ANNEX-WHS-001/002 + ANNEX-QMS-007/014/017 | Epicor transaction + M365 evidence | 7 | Governance / compliance record
frm-705 | frm-705-location-label.html | Nhãn vị trí | Warehouse/Cleanliness/Shipment | REBUILD | P2 | W4 | Phase 4 - Cleanliness, packaging, shipping | Warehouse + QA | WHS/QA/Production | Print label / card | Labels workbook pack | PACK-WHS-LABELS | Operational record | SOP-701 | WI-702 | ANNEX-WHS-001/002 + ANNEX-QMS-007/014/017 | Epicor transaction + M365 evidence | 7 | Governance / compliance record
frm-706 | frm-706-shipping-label.html | Nhãn giao hàng | Warehouse/Cleanliness/Shipment | REBUILD | P2 | W4 | Phase 4 - Cleanliness, packaging, shipping | Warehouse + QA | WHS/QA/Production | Print label / card | Labels workbook pack | PACK-WHS-LABELS | Operational record | SOP-703 | WI-206/WI-714 | ANNEX-WHS-001/002 + ANNEX-QMS-007/014/017 | Epicor transaction + M365 evidence | 9 | Governance / compliance record
frm-713 | frm-713-cleanroom-entry-and-gowning-log.html | Cleanroom Entry and Gowning Log | Warehouse/Cleanliness/Shipment | NEW | P2 | W4 | Phase 4 - Cleanliness, packaging, shipping | Warehouse + QA | WHS/QA/Production | Register / Log | Shared rolling workbook | PACK-WHS-ROLLING-LOGS | Gate / Hold / Release | SOP-702 | WI-711 | ANNEX-HSE-001 + ANNEX-QMS-017 | M365 evidence / shared workbook | 0 | Governance / compliance record | Needed only for controlled cleanroom/clean area entry discipline.
frm-714 | frm-714-ultrasonic-cleaning-batch-record.html | Ultrasonic Cleaning Batch Record | Warehouse/Cleanliness/Shipment | NEW | P2 | W4 | Phase 4 - Cleanliness, packaging, shipping | Warehouse + QA | WHS/QA/Production | Event form | Single template workbook | FRM-714 | Gate / Hold / Release | SOP-702 | WI-712 | ANNEX-QA-007 + ANNEX-WHS-001 | M365 evidence / shared workbook | 0 | Governance / compliance record | Needed for bath ID, chemistry, time, temperature, load, and verification evidence.
frm-715 | frm-715-vacuum-clean-build-and-bagging-record.html | Vacuum-Compatible Clean Build and Bagging Record | Warehouse/Cleanliness/Shipment | NEW | P2 | W4 | Phase 4 - Cleanliness, packaging, shipping | Warehouse + QA | WHS/QA/Production | Checklist / Gate | Single template workbook | FRM-715 | Gate / Hold / Release | SOP-702 | WI-716 | ANNEX-QA-007 + ANNEX-WHS-001 | M365 evidence / shared workbook | 0 | Governance / compliance record | Needed for vacuum/clean packaging build, purge, seal, and preservation evidence.
frm-721 | frm-721-fod-line-clearance-and-tool-accountability-log.html | FOD Line Clearance and Tool Accountability Log | Warehouse/Cleanliness/Shipment | NEW | P2 | W4 | Phase 4 - Cleanliness, packaging, shipping | Warehouse + QA | WHS/QA/Production | Checklist / Gate | Single template workbook | FRM-721 | Gate / Hold / Release | SOP-703 | WI-721 | ANNEX-QMS-017 + ANNEX-HSE-001 | M365 evidence / shared workbook | 0 | Direct KPI / bonus / promotion evidence | Needed for FOD-sensitive jobs and high-cleanliness zones.
frm-121 | frm-121-context-analysis-swot-pestle.html | Phân tích bối cảnh SWOT/PESTLE | QMS/System | REBUILD | P3 | W4 | Phase 4 - Cleanliness, packaging, shipping | QMS | QMS/Process Owner | Event form | Annual review workbook pack | PACK-QMS-ANNUAL-REVIEW | System control / governance | SOP-101/SOP-102 |  | ANNEX-QMS-001/002/011/024 | M365 evidence / shared workbook | 0 | Governance / compliance record
frm-122 | frm-122-interested-parties-register.html | Sổ các bên quan tâm | QMS/System | REBUILD | P3 | W4 | Phase 4 - Cleanliness, packaging, shipping | QMS | QMS/Process Owner | Register / Log | Annual review workbook pack | PACK-QMS-ANNUAL-REVIEW | System control / governance | SOP-101/SOP-102 |  | ANNEX-QMS-001/002/011/024 | M365 evidence / shared workbook | 0 | Governance / compliance record
frm-123 | frm-123-interested-party-requirements-register.html | Sổ yêu cầu của các bên quan tâm | QMS/System | REBUILD | P3 | W4 | Phase 4 - Cleanliness, packaging, shipping | QMS | QMS/Process Owner | Register / Log | Annual review workbook pack | PACK-QMS-ANNUAL-REVIEW | System control / governance | SOP-101/SOP-102 |  | ANNEX-QMS-001/002/011/024 | M365 evidence / shared workbook | 0 | Governance / compliance record
frm-124 | frm-124-climate-change-assessment-record.html | Hồ sơ đánh giá biến đổi khí hậu | QMS/System | REBUILD | P3 | W4 | Phase 4 - Cleanliness, packaging, shipping | QMS | QMS/Process Owner | Event form | Annual review workbook pack | PACK-QMS-ANNUAL-REVIEW | System control / governance | SOP-101/SOP-102 |  | ANNEX-QMS-001/002/011/024 | M365 evidence / shared workbook | 0 | Governance / compliance record
frm-125 | frm-125-customer-csr-register.html | Sổ CSR khách hàng | QMS/System | REBUILD | P3 | W4 | Phase 4 - Cleanliness, packaging, shipping | QMS | QMS/Process Owner | Register / Log | Annual review workbook pack | PACK-QMS-ANNUAL-REVIEW | System control / governance | SOP-101/SOP-102 |  | ANNEX-QMS-001/002/011/024 | M365 evidence / shared workbook | 0 | Governance / compliance record
frm-801 | frm-801-training-plan.html | Kế hoạch đào tạo | People/HSE/Finance | REBUILD | P2 | W5 | Phase 5 - People & management support | HR + Department Manager | HR/Supervisor | Event form | Training & competency workbook pack | PACK-HR-COMPETENCY | Operational record / KPI evidence | SOP-801 | WI-801/WI-804 | ANNEX-HR-001 + ANNEX-QMS-027/028 | M365 evidence / shared workbook | 9 | Governance / compliance record
frm-802 | frm-802-attendance-sheet.html | Danh sách tham dự | People/HSE/Finance | REBUILD | P2 | W5 | Phase 5 - People & management support | HR + Department Manager | HR/Supervisor | Event form | Training & competency workbook pack | PACK-HR-COMPETENCY | Operational record / KPI evidence | SOP-801 | WI-801/WI-804 | ANNEX-HR-001 + ANNEX-QMS-027/028 | M365 evidence / shared workbook | 8 | Governance / compliance record
frm-803 | frm-803-ojt-checklist.html | Checklist OJT | People/HSE/Finance | REBUILD | P2 | W5 | Phase 5 - People & management support | HR + Department Manager | HR/Supervisor | Checklist / Gate | Training & competency workbook pack | PACK-HR-COMPETENCY | Operational record / KPI evidence | SOP-801 | WI-801/WI-804 | ANNEX-HR-001 + ANNEX-QMS-027/028 | M365 evidence / shared workbook | 31 | Direct KPI / bonus / promotion evidence
frm-804 | frm-804-competency-assessment.html | Đánh giá năng lực | People/HSE/Finance | REBUILD | P2 | W5 | Phase 5 - People & management support | HR + Department Manager | HR/Supervisor | Event form | Training & competency workbook pack | PACK-HR-COMPETENCY | Operational record / KPI evidence | SOP-801 | WI-801/WI-804 | ANNEX-HR-001 + ANNEX-QMS-027/028 | M365 evidence / shared workbook | 16 | Direct KPI / bonus / promotion evidence
frm-805 | frm-805-level-certification.html | Chứng nhận bậc | People/HSE/Finance | REBUILD | P2 | W5 | Phase 5 - People & management support | HR + Department Manager | HR/Supervisor | Event form | Training & competency workbook pack | PACK-HR-COMPETENCY | Operational record / KPI evidence | SOP-801 | WI-801/WI-804 | ANNEX-HR-001 + ANNEX-QMS-027/028 | M365 evidence / shared workbook | 11 | Direct KPI / bonus / promotion evidence
frm-806 | frm-806-certification-tracking-log.html | Nhật ký theo dõi chứng nhận | People/HSE/Finance | REBUILD | P2 | W5 | Phase 5 - People & management support | HR + Department Manager | HR/Supervisor | Register / Log | Training & competency workbook pack | PACK-HR-COMPETENCY | Operational record / KPI evidence | SOP-801 | WI-801/WI-804 | ANNEX-HR-001 + ANNEX-QMS-027/028 | M365 evidence / shared workbook | 8 | Direct KPI / bonus / promotion evidence
frm-807 | frm-807-skill-matrix.html | Ma trận kỹ năng | People/HSE/Finance | REBUILD | P2 | W5 | Phase 5 - People & management support | HR + Department Manager | HR/Supervisor | Register / Log | Training & competency workbook pack | PACK-HR-COMPETENCY | Operational record / KPI evidence | SOP-801 | WI-801/WI-804 | ANNEX-HR-001 + ANNEX-QMS-027/028 | M365 evidence / shared workbook | 10 | Direct KPI / bonus / promotion evidence
frm-808 | frm-808-evaluation-template.html | Biểu mẫu đánh giá | People/HSE/Finance | REBUILD | P2 | W5 | Phase 5 - People & management support | HR + Department Manager | HR/Supervisor | Event form | Training & competency workbook pack | PACK-HR-COMPETENCY | Operational record / KPI evidence | SOP-801 | WI-801/WI-804 | ANNEX-HR-001 + ANNEX-QMS-027/028 | M365 evidence / shared workbook | 7 | Governance / compliance record
frm-809 | frm-809-skill-matrix-and-kpi.html | Ma trận kỹ năng and KPI | People/HSE/Finance | REBUILD | P2 | W5 | Phase 5 - People & management support | HR + Department Manager | HR/Supervisor | Register / Log | Training & competency workbook pack | PACK-HR-COMPETENCY | Operational record / KPI evidence | SOP-801 | WI-801/WI-804 | ANNEX-HR-001 + ANNEX-QMS-027/028 | M365 evidence / shared workbook | 17 | Direct KPI / bonus / promotion evidence
frm-103 | frm-103-document-issue-control.html | Kiểm soát phát hành tài liệu | QMS/System | CONDITIONAL_HARDCOPY | P4 | W5 | Phase 5 - People & management support | QMS | QMS/Process Owner | Register / Log | Shared rolling workbook | PACK-QMS-GOVERNANCE-REGISTERS | System control / governance | SOP-101/SOP-102 |  |  | M365 evidence / shared workbook | 0 | Governance / compliance record | Use only if controlled hardcopy remains in scope.
frm-108 | frm-108-controlled-copy-register.html | Sổ bản sao kiểm soát | QMS/System | CONDITIONAL_HARDCOPY | P4 | W5 | Phase 5 - People & management support | QMS | QMS/Process Owner | Register / Log | Shared rolling workbook | PACK-QMS-GOVERNANCE-REGISTERS | System control / governance | SOP-101/SOP-102 |  |  | M365 evidence / shared workbook | 0 | Governance / compliance record | Use only if controlled hardcopy remains in scope.
frm-901 | frm-901-internal-audit-checklist.html | Checklist đánh giá nội bộ | Audit/Management | REBUILD | P3 | W6 | Phase 6 - Audit, HR, finance, stabilization | QMS + Top Management | QMS/Auditor/Management | Checklist / Gate | Audit & management review workbook pack | FRM-901 | Gate / Hold / Release | SOP-901 |  | ANNEX-QMS-003/008/020/025/027 | M365 evidence / shared workbook | 6 | Indirect evidence / governance
frm-902 | frm-902-layered-process-audit-checklist.html | Checklist Layered Process Audit | Audit/Management | REBUILD | P3 | W6 | Phase 6 - Audit, HR, finance, stabilization | QMS + Top Management | QMS/Auditor/Management | Checklist / Gate | Audit & management review workbook pack | FRM-902 | Gate / Hold / Release | SOP-901 |  | ANNEX-QMS-003/008/020/025/027 | M365 evidence / shared workbook | 3 | Indirect evidence / governance
frm-911 | frm-911-management-review-minutes.html | Biên bản xem xét của lãnh đạo | Audit/Management | REBUILD | P3 | W6 | Phase 6 - Audit, HR, finance, stabilization | QMS + Top Management | QMS/Auditor/Management | Event form | Audit & management review workbook pack | FRM-911 | Gate / Hold / Release | SOP-902 |  | ANNEX-QMS-003/008/020/025/027 | M365 evidence / shared workbook | 9 | Indirect evidence / governance
frm-811 | frm-811-incident-report.html | Báo cáo sự cố | People/HSE/Finance | REBUILD | P3 | W6 | Phase 6 - Audit, HR, finance, stabilization | HSE | HSE/Supervisor | Event form | Single template workbook | FRM-811 | Operational record / KPI evidence | SOP-802 | WI-802 | ANNEX-HSE-001 + ANNEX-QMS-020 | M365 evidence / shared workbook | 13 | Direct KPI / bonus / promotion evidence
frm-812 | frm-812-lighting-log.html | Nhật ký chiếu sáng | People/HSE/Finance | REBUILD | P3 | W6 | Phase 6 - Audit, HR, finance, stabilization | HSE | HSE/Supervisor | Register / Log | Shared rolling workbook | PACK-HR-HSE-FIN-REGISTERS | Operational record / KPI evidence | SOP-802 | WI-802 | ANNEX-HSE-001 + ANNEX-QMS-020 | M365 evidence / shared workbook | 5 | Governance / compliance record
frm-821 | frm-821-invoice-request.html | Yêu cầu xuất hóa đơn | People/HSE/Finance | REBUILD | P3 | W6 | Phase 6 - Audit, HR, finance, stabilization | Finance | Finance/Sales | Event form | Single template workbook | FRM-821 | Operational record / KPI evidence | SOP-803 |  |  | Epicor transaction + M365 evidence | 11 | Governance / compliance record

## 03_OVERLAP_AUDIT
Overlap and boundary decisions
Quyết định boundary để không chồng lấn khi viết form.
ID | Overlap | Finding | Decision | Reason
OL-01 | FRM-412 vs FRM-701 | Cùng chức năng nhận hàng/IQC | Merge FRM-412 into FRM-701 | Tránh hai log nhận hàng song song
OL-02 | FRM-109 vs FRM-141/111 + ANNEX-QMS-025/IT-001 | Một cái là matrix governance, một cái là giao dịch truy cập | Convert FRM-109 to annex/transaction architecture | Không nhập tay lại ma trận quyền
OL-03 | FRM-401 vs Epicor PO master | Theo dõi PO master bằng Excel gây double entry | Redesign FRM-401 as expedite/exception log | Epicor vẫn là SoR cho PO
OL-04 | FRM-171 vs FRM-208 | Formal communication khác daily tier escalation | Tách rõ mục đích | Người dùng không dùng nhầm communication plan cho daily standup
OL-05 | FRM-204 vs FRM-519 | Kickoff PO/WO khác pre-run tại máy | Tách rõ | Không bỏ sót pre-run verification
OL-06 | FRM-707 vs FRM-709 vs FRM-715 | Đóng gói thường, đóng gói sạch, vacuum clean build là ba mức khác nhau | Giữ tách 3 form | Tránh checklist quá dài và mơ hồ
OL-07 | FRM-651 vs FRM-413 vs WI-606 evidence | Hold/disposition khác NCR khác reaction tại hiện trường | Giữ boundary hiện tại | Ai cũng biết khi nào giữ, khi nào mở NCR
OL-08 | FRM-641 vs FRM-642 | Inspection result khác ship/CoC register | Giữ tách | Kết quả đo không trộn với log phát hành
OL-09 | FRM-611/612/613 | Ba study khác nhau nhưng có thể gom chung physical workbook | One workbook pack, three logical forms | Giảm file rời nhưng không mất logic
OL-10 | FRM-807 vs FRM-809 | Skill matrix raw data khác management view + KPI | Giữ tách logical, gom chung workbook family | Vừa quản trị năng lực vừa hỗ trợ pay/promo
OL-11 | FRM-702 vs FRM-206 | Shipping checklist khác job completion checklist | Giữ tách | Một cái đóng job, một cái mở ship gate
OL-12 | FRM-403 vs FRM-404 vs FRM-411 | Yêu cầu outsource, dispatch checklist, incoming after outsource là ba điểm kiểm soát khác nhau | Giữ tách | Tránh mất flowdown hoặc miss incoming check

## 04_FIELD_LIBRARY
Field library
Chuẩn hóa tên trường, kiểu dữ liệu, nguồn dữ liệu, mức bắt buộc.
Field_Code | Field_Name | Data_Type | Meaning | Source_of_Truth | Mandatory | Applies_To
REC_ID | Record ID | Text | Unique ID / auto or manual | M365/Template | Yes | All
FORM_REV | Form revision | Text | Controlled template revision | QMS | Yes | All
RECORD_STATUS | Record status | List | DRAFT/OPEN/IN REVIEW/APPROVED/CLOSED/HOLD | Template list | Yes | All
PREPARED_BY | Prepared by | Text | Người lập | User | Yes | All
PREPARED_DT | Prepared date/time | DateTime | Ngày giờ lập | User | Yes | All
REVIEWED_BY | Reviewed by | Text | Người review | User | Conditional | All
APPROVED_BY | Approved by | Text | Người phê duyệt | User | Conditional | Gate forms
CUSTOMER | Customer | Text | Mã/Tên khách hàng | Epicor | Conditional | Commercial/Job
PO_NO | PO number | Text | Số PO/Contract | Epicor | Conditional | Commercial/Job
JOB_NO | Epicor job number | Text | Mã job/WO | Epicor | Conditional | Commercial/OPS/QA/WHS
PART_NO | Part number | Text | Mã part | Epicor/ENG | Conditional | Commercial/OPS/QA/WHS
DRAWING_NO | Drawing number | Text | Mã bản vẽ | ENG | Conditional | ENG/QA
DRAWING_REV | Drawing revision | Text | Rev bản vẽ/part | ENG/Epicor | Conditional | ENG/OPS/QA/WHS
QTY_ORDER | Ordered quantity | Number | Số lượng đặt | Epicor | Conditional | Commercial
QTY_ACCEPT | Accepted quantity | Number | Số lượng đạt | User | Conditional | QA/WHS
QTY_REJECT | Rejected quantity | Number | Số lượng loại | User | Conditional | QA/WHS
DUE_DATE | Due date | Date | Ngày giao cam kết | Epicor | Conditional | Commercial/Planning
WORKCENTER | Workcenter | List | Mã workcenter/cell | ANNEX-OPS-001 | Conditional | OPS/Planning
MACHINE_ID | Machine ID | List | Mã máy | ANNEX-ENG-001 | Conditional | OPS/MNT
PROGRAM_ID | Program ID | Text | Mã chương trình NC | ENG | Conditional | OPS/ENG
PROGRAM_REV | Program revision | Text | Rev chương trình NC | ENG | Conditional | OPS/ENG
FIXTURE_ID | Fixture/Jig ID | Text | Mã đồ gá | ENG/MNT | Conditional | OPS/ENG
TOOL_LIST_ID | Tool list ID | Text | Mã danh mục dao | ENG | Conditional | OPS
HEAT_LOT | Heat/Lot | Text | Số heat/lot vật liệu | Supplier cert | Conditional | PUR/WHS/QA
CERT_NO | Certificate number | Text | MTR/CoC/CoA/cert số | Supplier/QA | Conditional | PUR/WHS/QA
SAMPLING_PLAN | Sampling plan | List | AQL level / plan type | ANNEX-QA-001 | Conditional | QA
CTQ_FLAG | CTQ / special characteristic | List | Yes/No | Control Plan | Conditional | ENG/QA/OPS
HOLD_CODE | Hold code | List | Mã hold | ANNEX-QMS-020 / QA rules | Conditional | QA/WHS/OPS
DISPOSITION | Disposition | List | Use as is / Rework / Scrap / Return / Concession | QA | Conditional | QA
NC_NO | NCR number | Text | Số NCR | QA | Conditional | QA/OPS
CAPA_NO | CAPA number | Text | Số CAPA/8D | QA | Conditional | QA
PACK_NUM | Pack number | Text | Số kiện/pack | Epicor | Conditional | WHS/QA
SHIPMENT_NO | Shipment number | Text | Số shipment | Epicor | Conditional | WHS/QA
SSCC | SSCC | Text | Mã logistic unit GS1 | Label system | Conditional | WHS
COC_NO | CoC number | Text | Số chứng nhận phù hợp | QA | Conditional | QA/WHS
EVIDENCE_LINK | Evidence link | Text/URL | Đường dẫn hồ sơ M365 | M365 | Yes | All
EMPLOYEE_ID | Employee ID | Text | Mã nhân viên | HR | Conditional | HR/HSE
SKILL_LEVEL | Skill level | List | L0-L4 or defined company levels | ANNEX-HR-001 | Conditional | HR
CERT_LEVEL | Certification level | List | Authorized to work level | ANNEX-HR-001 | Conditional | HR

## 05_DESIGN_STANDARDS
Excel form design standards
Các rule bắt buộc khi build workbook template.
Rule_ID | Rule | Why | Applies_To
DS-01 | Một form chỉ phục vụ một hành vi nghiệp vụ chính | Tránh gom nhiều mục đích khác nhau vào cùng một form | Tất cả
DS-02 | Không dùng form để thay Epicor | Form chỉ ghi evidence/gate; transaction master vẫn ở Epicor | Commercial, OPS, QA, WHS
DS-03 | M365/SharePoint là SSOT cho file evidence | File form đã điền, scan, ảnh, PDF, CoC, cert phải nằm ở SSOT | Tất cả
DS-04 | Excel template không dùng macro | Ưu tiên data validation, protection, table, drop-down; tránh VBA để dễ kiểm soát | Tất cả
DS-05 | Một mã trạng thái dùng xuyên hệ thống | PASS/HOLD/REJECT/N/A; OPEN/IN PROGRESS/CLOSED; MINOR/MAJOR/CRITICAL | Tất cả
DS-06 | Ô nhập liệu màu xanh, ô logic màu đen | Người dùng nhìn là biết ô nào phải nhập | Tất cả
DS-07 | Không để người dùng tự sửa công thức/heading | Chỉ mở ô nhập và vùng table cần điền | Tất cả
DS-08 | Mọi form phải có trường người nhập, thời gian, owner, revision | Đủ truy xuất và trách nhiệm | Tất cả
DS-09 | Mọi form gate phải có decision rõ | APPROVE / APPROVE WITH CONDITION / HOLD / REJECT | Gate forms
DS-10 | Mọi checklist bắt buộc dùng OK / NG / N/A | Không để ô trống gây tranh cãi | Checklist
DS-11 | Log/register phải dùng table chuẩn | Có filter, sort, data validation, cột evidence link | Logs
DS-12 | Label/print form phải có print area cố định | Không để mỗi người in mỗi kiểu | Labels
DS-13 | Study pack gom vào workbook family | GRR/Bias/Linearity/Attribute MSA dùng pack để giảm file rời | Metrology
DS-14 | Training/competency gom vào workbook family | Để HR kiểm soát thống nhất và trích KPI dễ hơn | HR
DS-15 | Không duplicate cùng một trường master ở nhiều form nếu có thể link tham chiếu | Ví dụ Part No, Rev, Job No lấy từ SoR và copy tối thiểu | Tất cả
DS-16 | Field bắt buộc phải có validation list hoặc rule rõ | Giảm nhập liệu tự do | Tất cả
DS-17 | Mọi form phải nói rõ trigger sử dụng | Ai mở form khi nào phải rõ | Tất cả
DS-18 | Mọi form phải nói rõ retention class | Giữ bao lâu, theo event nào, legal hold hay không | Tất cả
DS-19 | Mọi form phải map về SOP/WI/ANNEX/JD | Không có form mồ côi | Tất cả
DS-20 | Mọi form dùng cho thưởng-thăng chức phải có guardrail | Không cho dùng số liệu khi record thiếu bằng chứng hoặc sai owner | HR/KPI

## 06_PERFORMANCE_MAP
Performance, pay, bonus, promotion evidence map
Các form nào được phép dùng làm evidence cho đánh giá nhân sự.
Role | Evidence_Forms | Primary_Measures | Use_for_PayBonusPromotion | Guardrail
Production Operator | FRM-511, FRM-512, FRM-513, FRM-651, FRM-721 | First-piece pass, downtime discipline, tool-life discipline, quality escapes, FOD discipline | Direct | Không dùng KPI nếu thiếu traveler/first-piece/NCR evidence
Setup Technician | FRM-302, FRM-511, FRM-514, FRM-518, FRM-519 | Setup accuracy, changeover time, transfer validation, pre-run discipline | Direct | Không thưởng tốc độ nếu first-piece fail hoặc bypass gate
Planner/Dispatcher | FRM-501, FRM-502, FRM-503, FRM-504, FRM-208, FRM-209 | Dispatch adherence, WIP aging, handover quality, escalation discipline | Direct | Không tính on-time nếu due date bị sửa không phê duyệt
QA Inspector | FRM-621, FRM-631, FRM-641, FRM-651, FRM-701 | Sampling discipline, inspection accuracy, release discipline, containment speed | Direct | Không dùng KPI nếu measurement/gage status không hợp lệ
QA Engineer | FRM-611, FRM-612, FRM-613, FRM-652, FRM-653 | MSA capability, corrective action quality, systemic improvement | Direct | Không chấm cao nếu CAPA đóng mà tái diễn
Purchasing | FRM-402, FRM-405, FRM-406, FRM-408, FRM-409, FRM-403 | Supplier quality, response time, flowdown discipline, outsourcing control | Direct | Không đánh giá chỉ theo giá/OTD nếu thiếu quality evidence
Warehouse | FRM-701, FRM-702, FRM-703, FRM-707, FRM-709, FRM-712, FRM-721 | Receiving accuracy, pack accuracy, traceability, clean pack discipline | Direct | Không thưởng nếu ship đúng nhưng thiếu traceability/pack evidence
Maintenance | FRM-521, FRM-522, FRM-523, FRM-524 | PM completion, breakdown response, asset history discipline | Direct | Không tính PM completion nếu checklist ký khống
Engineer | FRM-301, FRM-303, FRM-304, FRM-305, FRM-306, FRM-311 | Quote accuracy, DFM quality, release quality, FAI readiness | Indirect | Không dùng productivity đơn thuần nếu release gây rework
HR / Dept Manager | FRM-803, FRM-804, FRM-805, FRM-806, FRM-807, FRM-809 | Competency growth, certification, skill coverage, KPI readiness | Direct | Promotion must require certification + sustained performance evidence

## 99_SOURCES
Research sources
Official sources used for architecture decisions.
Source | URL | Used_For
ISO revision update | https://committee.iso.org/sites/tc176sc2/home/news/content-left-area/news-and-updates/iso-9001-revision-update-3.html | Status of ISO 9001 revision in Feb 2026
APG Processes | https://committee.iso.org/files/live/sites/tc176/files/PDF%20APG%20New%20Disclaimer%2012-2023/ISO-TC%20176-TF_APG-Processes.pdf | Process approach and documented information in practice
APG Digital Processes | https://committee.iso.org/files/live/sites/tc176/files/PDF%20APG%20New%20Disclaimer%2012-2023/ISO-TC%20176-TF_APG-Digital_Processes.pdf | Digital workflow and evidence discipline
APG External Providers | https://committee.iso.org/files/live/sites/tc176/files/PDF%20APG%20New%20Disclaimer%2012-2023/ISO-TC%20176-TF_APG-ExternalProviders.pdf | Risk-based control of external providers
ISO 10013:2021 | https://www.iso.org/standard/75171.html | Guidance for documented information and forms/records architecture
ISO 10015:2019 | https://www.iso.org/standard/69459.html | Competence management and people development
IAQG SCMH overview | https://scmh.iaqg.org/wp-content/uploads/2024/08/SCMH-Communication-Pack-21AUG2024-2.pdf | Manufacturing work instructions, KPI, gemba, product safety topics
IA9100 key changes | https://iaqg.org/wp-content/uploads/2019/10/IA9100-Key-Changes-Clause-View.pdf | Product safety, counterfeit, human factors, configuration themes
9100 clarifications | https://iaqg.org/wp-content/uploads/2023/04/9100-2016-Series-Clarification-Table-2024-02-12.pdf | Clarifications for supplier control, management review, human factors
GS1 Logistic Label Guideline | https://www.gs1.org/docs/tl/GS1_Logistic_Label_Guideline.pdf | Logistic label, SSCC, pack labeling
GS1 SSCC | https://www.gs1.org/standards/id-keys/sscc | Definition and use of SSCC
SEMI E10 | https://www.semi.org/en/Standards/CTR_031244 | RAM/OEE language for semiconductor manufacturing
SEMI E78 | https://store-us.semi.org/products/e07800-semi-e78-guide-to-assess-and-control-electrostatic-discharge-esd-and-electrostatic-attraction-esa-for-equipment | ESD/ESA control for semiconductor equipment/environment